## Slide 1
Proposal for Accounting, Controller and CFO Services
October 5, 2026
PREPARED FOR
AJAC, Inc. dba George Brazil Plumbing & Electrical
3830 S 38th St, Phoenix, AZ 85040
Attn: Marc Erpenbeck, President
PREPARED BY
Steven Nikolov, Principal
steven@onyxcfo.com | direct 480-999-5509 | mobile 480-772-5612
Josephine Mack, Chief of Staff and Client Relations
jmack@onyxcfo.com
Onyx Accounting Group, LLC | 14614 N Kierland Blvd, Suite N220, Scottsdale, AZ 85254 | onyxcfo.com
Notes: Cover. Proposal accompanies the engagement letter dated October 5, 2026.

## Slide 2: A note to Marc and the leadership team
INTRODUCTION
October 5, 2026
Marc Erpenbeck, President
AJAC, Inc. dba George Brazil
3830 S 38th St
Phoenix, AZ 85040
Dear Marc,
Thank you for the time you, Shawne, Josh and Ian gave us at your office on October 2. This proposal accompanies the enclosed engagement letter and describes how Onyx Accounting Group would support George Brazil following your CFO's departure.
We have organized it around what we heard. The first priority is continuity: keeping the monthly close, Bell Bank reporting and the day-to-day accounting on track while supporting and training Ian. Behind that sits the work that needs controller and CFO judgment, including the 401(k) plan audit, the year-end financial audit, a smoother accounts payable process, cleaner flows between ServiceTitan, QStock and Sage Intacct, and planning for the S corporation conversion in 2028.
Our fees are hourly at the rates in Section 05. You pay for the hours worked, and the mix of controller, CFO and staff time can be changed by email as your needs change. There is no minimum term.
We would welcome the opportunity to work with your team and are glad to meet again to walk through any part of this proposal.
Steven Nikolov
Principal, Onyx Accounting Group

## Slide 3: What this proposal covers
CONTENTS
01
Who we are
The firm, how we staff an engagement, and your engagement team
02
What we can help with
Our understanding of George Brazil, the services proposed, and how we will work together
03
Engagement timeline
Key dates from kickoff through the year-end audit
04
30/60/90-day plan
What happens in each phase and what you receive at each checkpoint
05
Proposed fees
Hourly rates, billing terms and how we manage the budget
06
Why ONYX and next steps
What a team gives you that a single hire cannot, and how we start

## Slide 4: Onyx Accounting Group
01 WHO WE ARE
Onyx Accounting Group is a Scottsdale, Arizona accounting firm that provides bookkeeping, controller and CFO services to privately held companies. We work inside our clients' own systems, including Sage Intacct and QuickBooks, as an extension of their finance team, and we are built to cover the full range from transaction detail to the owner's table.
1
Big-firm background
Our leadership held Director and Manager roles at top 10 national accounting firms and brings that standard of review and documentation to privately held companies.
2
Industry experience
Construction and the trades, real estate and property management, professional services, distribution and retail, and hospitality.
3
Ownership structures
Owner-led, private equity backed and family office companies, including lender, investor and audit reporting.
How we staff an engagement
Scottsdale team
Engagement leadership, the controller and CFO roles, every judgment call, and on-site time in Phoenix for onboarding and training.
Supporting staff
Reconciliations, schedules and transaction support prepared on our systems by accountants with ten or more years of experience, and reviewed in Scottsdale.
Perform and review
The person who prepares a number is never the person who approves it. Every reconciliation, journal entry and report is reviewed by a second accountant before it reaches you.
One file, not one person
Procedures, the close checklist and the open-items list live in a shared file your team can see, so nothing depends on a single individual.

## Slide 5: Your engagement team
01 WHO WE ARE
The principal leads the engagement and stays on it. Jessica Bumphus, who joined us at the October 2 meeting, leads the controller work. Staff support is assigned at kickoff, and the mix is adjusted with you as the work settles.
Team member | Role on this engagement | Responsibilities | Involvement
Steven Nikolov Principal | Engagement lead and CFO | Overall direction and quality. CFO-level work: close design, Bell Bank and management reporting, budgeting and forecasting, banking and covenant matters, S corporation conversion planning, direction to the finance team. | On site for kickoff. Weekly during the first 90 days, then at the monthly review and as needed.
Josephine Mack Chief of Staff and Client Relations | Client relations and staffing | Scheduling, staffing and client service. Your contact for anything about the engagement itself: scope changes, invoices, access and timing. | Throughout the engagement.
Jessica Bumphus Controller | ONYX controller | Leads the monthly close, reviews Ian's work and the reconciliations, prepares the Bell Bank quarterly package and management reporting, and drives the AP and systems improvements. | Weekly. On site in Phoenix for onboarding and training, remote otherwise.
ONYX Staff Accountant(s) | Staff support | Reconciliations, supporting schedules, depreciation, job-costing and inventory entries, audit request lists and data work, all under controller review. | As the monthly scope requires.
Your team keeps approval authority over payments, vendors, customers and payroll. ONYX works from view access to bank and loan accounts and from the access you grant in Sage Intacct, ServiceTitan, QStock and payroll.

## Slide 6: Our understanding of George Brazil
02 WHAT WE CAN HELP WITH
The company
AJAC, Inc. dba George Brazil Plumbing & Electrical, Phoenix. Residential plumbing and electrical service, in Arizona since 1990 and part of a name in home services that dates to 1955. Employee-owned through an ESOP.
Finance team. Marc Erpenbeck, President. Ian, in-house accountant, runs the day-to-day. The CFO departed on October 2.
Systems. Sage Intacct (general ledger), ServiceTitan (field service and point of sale), QStock (inventory), BambooHR and TRAX (HR and weekly payroll), Bill.com under evaluation for AP.
Banking and structure. Bell Bank, with quarterly reporting. C corporation today, with a planned conversion back to an S corporation in 2028. Annual financial audit and a 401(k) plan audit.
What you asked for
1
Continuity of the finance function now, without waiting for a hire to ramp up.
2
Controller leadership of the monthly close, with review of the day-to-day work and training for Ian.
3
Management and Bell Bank reporting that is accurate and on time.
4
Less manual work between ServiceTitan, QStock and Sage Intacct, and a smoother accounts payable process.
5
CFO guidance on budgeting, forecasting, the audits and the 2028 S corporation conversion.
Dates that do not wait
Oct 15
401(k) plan audit deadline
Nov 14
Bell Bank third-quarter reporting
Now
Completed tax return to your preparer for filing
Monthly
Close, management reporting and weekly payroll and benefit submissions continue uninterrupted
Dec 31
Year-end close, then the financial audit
Based on our October 2 meeting with Marc, Shawne, Josh and Ian and the materials provided afterward. Details are confirmed during onboarding.

## Slide 7: Services proposed for George Brazil
02 WHAT WE CAN HELP WITH
Controller services
Lead the monthly close on an agreed calendar
Review bank, credit card and loan reconciliations and journal entries
Review accounts payable (check run, positive pay) and accounts receivable, collections and deposits
Maintain depreciation schedules
Support job-costing and inventory entries at month end
Document procedures and simplify the chart of accounts
Management and bank reporting
Monthly management and departmental reporting in the format you use today
Bell Bank quarterly package and routine bank requests
Key business metrics reviewed with management each month
Cash flow monitoring so you know what is coming in and going out
CFO advisory
Budgeting, forecasting and scenario planning
Banking, lender and covenant reporting and negotiations
Accounting policy and reporting structure
Direction to the finance team as it is rebuilt
Planning and support for the 2028 S corporation conversion
Systems and process
Streamline accounts payable, in Bill.com or within Sage Intacct
Reduce manual steps and bottlenecks between ServiceTitan, QStock and Sage Intacct
Support your inventory project and the QStock integration; your team leads the project
Build review controls into the new workflows
Audit, tax and payroll support
Prepare schedules and answer requests for the 401(k) plan audit and the financial audit
Organize everything your tax preparer needs; ONYX does not prepare or file tax returns
Support weekly payroll and benefit submissions as needed
The scope mirrors Section 1 of the engagement letter dated October 5, 2026. Services can be added, reduced or paused by email.

## Slide 8: How we will work together
02 WHAT WE CAN HELP WITH
How ONYX operates
Work inside your Sage Intacct, with view access to bank, credit card and loan accounts
Perform and review on every reconciliation, entry and report
Weekly progress and budget update during the first 90 days, then a monthly review with Marc
On site in Phoenix for onboarding and training; remote for routine work
Procedures, close checklist and open items kept in one shared file
Automation used where it saves your team time, with human review of every material output
What stays with George Brazil
Approval of every payment, new vendor, new customer and payroll run
Signing authority and bank access; ONYX does not move funds
Ownership of the financial statements and management decisions
Tax filings, through your tax preparer
Leadership of the inventory project, with ONYX supporting the accounting and the Sage Intacct integration
A named internal owner for the engagement and timely answers from the team
Outside this proposal
Preparing or filing tax returns
Performing the financial or 401(k) audits; we support them and give no opinion or assurance
Forensic or fraud investigation; anything irregular is escalated to you in writing and handled as a separate engagement
Holding signing authority or moving money
Communication. Weekly progress and budget update during the first 90 days. Monthly review of results with Marc. Quarterly review of scope, staffing mix and fees. Annual planning session before the budget year.
These responsibilities match the "How we'll work together" section of the engagement letter.

## Slide 9: October 2026 through March 2027
03 ENGAGEMENT TIMELINE
Oct 2026
Nov
Dec
Jan 2027
Feb
Mar
Kickoff, access and knowledge capture
401(k) plan audit support (Oct 15)
Monthly close led and reviewed by ONYX
Bell Bank Q3 package (Nov 14)
Training and review of day-to-day work
AP streamlining and chart of accounts cleanup
ServiceTitan, QStock and Intacct workflow mapping
2027 budget and forecast framework
Year-end close and financial audit support
CFO reporting rhythm and 2028 S corporation planning
Kickoff
Day 30 review
Day 60 review
Day 90 review
Steady state
Checkpoints
Assumes a start the week of October 12, 2026 with system access from day one. Red bars are fixed external deadlines. Dates are confirmed with Marc in the first week.

## Slide 10: The first 90 days
04 30/60/90-DAY PLAN
Days 1 to 30
Stabilize
Activities
Kickoff with Marc and Ian; access to Sage Intacct, ServiceTitan, QStock, payroll and bank view
Capture the departed CFO's recurring tasks, files, deadlines and bank contacts
Support the 401(k) plan audit and get the completed return to your preparer
Begin on-site training with Ian and take over review of the close
What you have at the checkpoint
Close calendar and task list documented
September close reviewed, October close under way
Audit requests answered on time
Days 31 to 60
Standardize
Activities
Lead the October close and deliver management reporting
Prepare and deliver the Bell Bank third-quarter package
Review AP, positive pay and AR processes; decide Bill.com versus Sage Intacct for AP
Map the ServiceTitan, QStock and Sage Intacct flows and log the gaps with owners
What you have at the checkpoint
First ONYX-reviewed close and reporting pack
Bell Bank package submitted
Process map with gaps and owners
Days 61 to 90
Improve
Activities
Implement the AP changes and simplify the chart of accounts
Year-end close plan and audit request list prepared
2027 budget framework and the metrics management will track
90-day review with Marc: results, staffing mix and the plan for 2027
What you have at the checkpoint
Documented close and reporting procedures
Year-end and audit plan agreed
2027 budget framework and steady-state staffing agreed
Day 91 onward. Monthly close and reporting rhythm, quarterly Bell Bank package, budget versus actual, CFO support including the 2028 S corporation planning. The staffing mix is adjusted by email as needs change.

## Slide 11: What you receive, and when
04 30/60/90-DAY PLAN
Cadence | Deliverable | Prepared by | Reviewed by
Weekly, first 90 days | Progress and budget update; open-items list with owners and dates | Controller | Principal
Weekly | Payroll and benefit submission support as needed; AP check run and positive-pay file reviewed before release | Staff | Controller
Monthly | Close completed on the agreed calendar; reconciliations and journal entries reviewed; management and departmental reporting; cash flow view; metrics reviewed with management | Staff and Controller | Controller and Principal
Quarterly | Bell Bank reporting package; review of scope, staffing mix and fees with Marc | Controller | Principal
Annually | Year-end close; schedules and responses for the financial audit and the 401(k) plan audit; tax preparer package; budget and forecast for the coming year | Controller | Principal
Ongoing | Procedures, close checklist and chart of accounts kept current in one shared file; training notes for Ian | Controller | Principal
Every deliverable is prepared by one person and reviewed by another before it reaches you. Reports are tied to the ledger in Sage Intacct.

## Slide 12: Hourly rates and billing terms
05 PROPOSED FEES
Fees are hourly, billed as incurred. You pay for the hours worked, and the mix of staff, controller and CFO time is set with you and changed by email.
Role | Hourly rate | Typical use on this engagement
Staff Accountant | $100 | Reconciliations, supporting schedules, depreciation, job-costing and inventory entries, audit request lists
Controller | $185 | Monthly close, review of Ian's work, Bell Bank and management reporting, AP and systems improvements, training
CFO | $275 | Budgeting and forecasting, banking and lender matters, accounting policy, S corporation conversion planning, direction to the finance team
Rates are guaranteed through December 31, 2026. After that date, rates change only as agreed in writing.
Billing terms
Invoices every two weeks with time detail by person and task; net 7 days
Retainer of $3,000 before services begin, applied to the first invoice
Out-of-pocket costs such as travel time and meals billed at cost
No minimum term; either party may end the engagement on 30 days' written notice
Managing the budget
Weekly progress and budget update during onboarding
We advise you before any work that would substantially increase fees
Scope and staffing changes take effect once confirmed by email; no new letter or signature
Not included. Tax return preparation and filing, which your tax preparer handles, and performing the audits, which we support but do not perform. Full terms are in Section 2 of the engagement letter.

## Slide 13: What a team gives you, and how we start
06 WHY ONYX AND NEXT STEPS
Compared with a single full-time hire
1
Continuity
You work with a team, not one individual. If a person changes, the file, the procedures and your senior contact do not.
2
Depth
CFO, controller and staff expertise under one engagement, with a built-in review process so the work is completed accurately and consistently.
3
Flexibility
Phase work in, pause a project, scale back or expand by email. No penalties and no paperwork to redo. You pay only for hours worked.
4
Fit
We work alongside Ian, your tax preparer, your auditor and Bell Bank, and we keep approvals with you. Stabilizing a close and the systems behind it is what we do every day.
Next steps
1
Review
Share this proposal and the engagement letter with Shawne, Josh and Ian. We are glad to join a follow-up call to answer questions.
2
Sign
Sign the engagement letter; we can send it for electronic signature. The $3,000 retainer starts the engagement.
3
Grant access
Sage Intacct, ServiceTitan, QStock, BambooHR and TRAX, Bell Bank view access, the close files and the 401(k) audit request list.
4
Kick off
On site in Phoenix the following week. Knowledge capture, training with Ian and the first weekly update begin in week one.
Steven Nikolov, Principal | steven@onyxcfo.com | direct 480-999-5509 | mobile 480-772-5612
Josephine Mack, Chief of Staff and Client Relations | jmack@onyxcfo.com

## Slide 14
Thank you
We appreciate the opportunity to earn George Brazil's business and to become a trusted partner to your team.
Onyx Accounting Group, LLC
14614 N Kierland Blvd, Suite N220
Scottsdale, AZ 85254
onyxcfo.com
Prepared for AJAC, Inc. dba George Brazil
Marc Erpenbeck, President